## Sheet1
Project Tracking Matrix
|  | PROJECT NAME | PRODUCT OWNER | START DATE | END DATE |  | OVERALL PROGRESS |  | PROJECT DELIVERABLE | StudiBuddi will allow students to connect with other students to help each other get help in similar courses, develop studying habits, and expand their network amongst students
|  | StudiBuddi | Tanner M. | 2020-01-22 | N/A |  | 5% |  | SCOPE STATEMENT | Sprint #1 - Sprint Planning, PRD, ADD, update BRD, database design
| AT RISK | TASK NAME | TASK TYPE | RESPONSIBLE | STORY POINTS | START | FINISH | DURATION (DAYS) | STATUS | COMMENTS
|  | Sprint 0 |  |  |  | 2020-02-03 | 2020-02-19 | 14 | Complete
|  | Sprint Planning Meeting | Planning | All team members | 3 | 2020-02-03 | 2020-02-03 | 0 | Complete
|  | PrelimBRDPresentation | Presentation | All team members | 5 | 2020-02-03 | 2020-02-05 | 2 | Complete
| x | BRD - Preface | BRD Section | Hunter D. | 2 | 2020-02-07 | 2020-02-07 | 0 | Complete
| x | BRD - Strategy | BRD Section | Oscar G. | 3 | 2020-02-10 | 2020-02-10 | 0 | Complete
|  | BRD - Market Segments | BRD Section | Oscar G. | 2 | 2020-02-10 | 2020-02-10 | 0 | Complete
|  | BRD - Primary Market Research | BRD Section | Hunter D. | 5 | 2020-02-11 | 2020-02-11 | 0 | Complete
|  | BRD - Secondary Market Research | BRD Section | Tanner M. | 5 | 2020-02-09 | 2020-02-10 | 1 | Complete
|  | BRD - Case Study | BRD Section | Luke K. | 3 | 2020-02-10 | 2020-02-10 | 0 | Complete
| x | BRD - Data Driven Decisions | BRD Section | Tanner M. | 3 | 2020-02-10 | 2020-02-10 | 0 | Complete
| x | BRD - User Need | BRD Section | Hunter D. | 5 | 2020-02-10 | 2020-02-12 | 2 | Complete
|  | BRD - Competitors | BRD Section | Tanner M., Hunter D. | 3 | 2020-02-10 | 2020-02-10 | 0 | Complete
| x | BRD - SWOT Analysis | BRD Section | Tymee K. | 5 | 2020-02-11 | 2020-02-11 | 0 | Complete
|  | BRD - Appendix | BRD Section | Oscar G. | 3 | 2020-02-10 | 2020-02-10 | 0 | Complete
|  | MP - Gantt Chart | Management plan | Hunter D. | 5 | 2020-02-17 | 2020-02-17 | 0 | Complete
|  | MP - Project Tracking Matrix | Management plan | Tanner M. | 5 | 2020-02-16 | 2020-02-16 | 0 | Complete
|  | MP - Sprint Board | Management plan | Hunter D. | 3 | 2020-02-17 | 2020-02-17 | 0 | Complete
|  | MP - Burndown Chart | Management plan | Tanner M. | 3 | 2020-02-16 | 2020-02-16 | 0 | Complete
|  | MP - Sprint Restrospective | Management plan | Oscar G. | 5 | 2020-02-16 | 2020-02-16 | 0 | Complete
|  | PRD - Goals | PRD | Oscar G. | 5 | 2020-03-07 | 2020-03-07 | 0 | Complete
|  | User Personas | PRD | Luke K. | 5 | 2020-03-07 | 2020-03-10 | 0 | Complete
|  | User Stories | PRD | Tymee K. | 5 | 2020-03-08 | 2020-03-12 | 0 | Complete
|  | Server Sitemap | PRD | Tanner M. | 5 | 2020-03-07 | 2020-03-07 | 0 | Complete
|  | Page Description | PRD | Tanner M. & Hunter D. | 5 | 2020-03-07 | 2020-03-07 | 0 | Complete
|  | Wireframes | PRD | Oscar G. | 5 | 2020-03-07 | 2020-03-12 | 0 | Complete
|  | Interfaces | PRD | Hunter D. | 5 | 2020-03-07 | 2020-03-07 | 0 | Complete
|  | Additional Functional Requirements | PRD | Tymee K. | 5 | 2020-03-08 | 2020-03-12 | 0 | Complete
|  | Non-Functional Requirements | PRD | Tymee K. | 5 | 2020-03-08 | 2020-03-12 | 0 | Complete
|  | Performance Requirements | PRD | Tymee K. | 5 | 2020-03-08 | 2020-03-10 | 0 | Complete
|  | Future Iterations | PRD | Luke K. | 5 | 2020-03-08 | 2020-03-12 | 0 | Complete
|  | API Diagram | ADD | Hunter D. | 5 | 2020-03-14 | 2020-03-14 | 0 | Complete
|  | Languages Diagram | ADD | Hunter D. | 5 | 2020-03-14 | 2020-03-14 | 0 | Complete
|  | Deployment Diagram | ADD | Tanner M. | 5 | 2020-03-14 | 2020-03-14 | 0 | Complete
|  | Class Diagram | ADD | Oscar G. | 5 | 2020-03-14 | 2020-03-14 | 0 | Complete
|  | Use case diagram | ADD | Luke K. | 5 | 2020-03-15 | 2020-03-15 | 0 | Complete
|  | Activity diagram | ADD | Oscar G. | 5 | 2020-03-15 | 2020-03-15 | 0 | Complete
|  | Tradeoff Analysis - Mobile vs. web | ADD | Hunter D. | 5 | 2020-03-14 | 2020-03-14 | 0 | Complete
|  | Tradeoff Analysis - Android vs. iOS | ADD | Oscar G. | 5 | 2020-03-14 | 2020-03-14 | 0 | Complete
|  | Tradeoff Analysis - Database | ADD | Tanner M. | 5 | 2020-03-14 | 2020-03-14 | 0 | Complete
|  | Risk Management | ADD | Tymee K. | 5 | 2020-03-15 | 2020-03-15 | 0 | Complete
|  | Sprint 1 Planning Meeting | Sprint Planning | All team members | 5 | 2020-02-24 | 2020-02-24 | 0 | Complete
|  | Update BRD | BRD Section | Tymee K. & Luke K. | 5 | - | - | 0 | Incomplete
|  | Implement Database | Code | Tanner M. & Oscar G. | 5 | - | - | 0 | Incomplete