## Agile Project Plan
Project Tracking Matrix
|  | PROJECT NAME | PRODUCT OWNER | START DATE | END DATE |  | OVERALL PROGRESS |  | PROJECT DELIVERABLE
|  | Pingr | Hunter D. | 2020-01-22 | N/A |  | 5% |  | SCOPE STATEMENT
| AT RISK | TASK NAME | TASK TYPE | RESPONSIBLE | STORY POINTS | START | FINISH | DURATION (DAYS) | STATUS | COMMENTS
|  | Sprint 0 |  |  |  | 2020-02-03 | 2020-02-19 | 14 | Complete
|  | Sprint Planning Meeting | Planning | All team members | 3 | 2020-02-03 | 2020-02-03 | 0 | Complete
|  | PrelimBRDPresentation | Presentation | All team members | 5 | 2020-02-03 | 2020-02-05 | 2 | Complete
|  | BRD - Preface | BRD Section | Hunter D. | 2 | 2020-02-07 | 2020-02-07 | 0 | Complete
|  | BRD - Strategy | BRD Section | Oscar G. | 3 | 2020-02-10 | 2020-02-10 | 0 | Complete
|  | BRD - Market Segments | BRD Section | Oscar G. | 2 | 2020-02-10 | 2020-02-10 | 0 | Complete
|  | BRD - Primary Market Research | BRD Section | Hunter D. | 5 | 2020-02-11 | 2020-02-11 | 0 | Complete
|  | BRD - Secondary Market Research | BRD Section | Tanner M. | 5 | 2020-02-09 | 2020-02-10 | 1 | Complete
|  | BRD - Case Study | BRD Section | Luke K. | 3 | 2020-02-10 | 2020-02-10 | 0 | Complete
|  | BRD - Data Driven Decisions | BRD Section | Tanner M. | 3 | 2020-02-10 | 2020-02-10 | 0 | Complete
|  | BRD - User Need | BRD Section | Hunter D. | 5 | 2020-02-10 | 2020-02-12 | 2 | Complete
|  | BRD - Competitors | BRD Section | Tanner M., Hunter D. | 3 | 2020-02-10 | 2020-02-10 | 0 | Complete
|  | BRD - SWOT Analysis | BRD Section | Tymee K. | 5 | 2020-02-11 | 2020-02-11 | 0 | Complete
|  | BRD - Appendix | BRD Section | Oscar G. | 3 | 2020-02-10 | 2020-02-10 | 0 | Complete
|  | Feature 3 |  | Jacob S. |  | 2022-09-09 | 2022-09-13 | 4 | Overdue
|  | Sprint 2 |  | Jacob S. |  | 2022-09-16 | 2022-09-24 | 8 | In Progress
|  | Feature 4 |  | Alex B. |  | 2022-09-16 | 2022-09-17 | 1 | In Progress
|  | Feature 5 |  | Frank C. |  | 2022-09-17 | 2022-09-21 | 4 | Not Started
|  | Feature 6 |  | Shari W. |  | 2022-09-22 | 2022-09-24 | 2 | Not Started
|  | Sprint 3 |  | Shari W. |  | 2022-09-25 | 2022-10-05 | 10 | Not Started
|  | Feature 7 |  | Alex B. |  | 2022-09-25 | 2022-09-29 | 4 | Not Started
|  | Feature 8 |  | Kennedy K. |  | 2022-09-24 | 2022-10-02 | 8 | Not Started
|  | Feature 9 |  | Jacob S. |  | 2022-10-02 | 2022-10-05 | 3 | Not Started