## Agile Project Plan
Project Tracking Matrix
|  | PROJECT NAME | PRODUCT OWNER | START DATE | END DATE |  | OVERALL PROGRESS |  | PROJECT DELIVERABLE
|  | Pingr | Hunter D. | 2020-01-22 | N/A |  | 5% |  | SCOPE STATEMENT
| AT RISK | TASK NAME | TASK TYPE | RESPONSIBLE | STORY POINTS | START | FINISH | DURATION (DAYS) | STATUS | COMMENTS
|  | Sprint 0 |  |  |  | 2020-02-03 | 2020-02-19 | 14 | Complete
|  | Sprint Planning Meeting | Planning | All team members | 3 | 2020-02-03 | 2020-02-03 | 0 | Complete
|  | PrelimBRDPresentation | Presentation | All team members | 5 | 2020-02-03 | 2020-02-05 | 2 | Complete
|  | Feature 3 |  | Jacob S. |  | 2022-09-09 | 2022-09-13 | 4 | Overdue
|  | Sprint 2 |  | Jacob S. |  | 2022-09-16 | 2022-09-24 | 8 | In Progress
|  | Feature 4 |  | Alex B. |  | 2022-09-16 | 2022-09-17 | 1 | In Progress
|  | Feature 5 |  | Frank C. |  | 2022-09-17 | 2022-09-21 | 4 | Not Started
|  | Feature 6 |  | Shari W. |  | 2022-09-22 | 2022-09-24 | 2 | Not Started
|  | Sprint 3 |  | Shari W. |  | 2022-09-25 | 2022-10-05 | 10 | Not Started
|  | Feature 7 |  | Alex B. |  | 2022-09-25 | 2022-09-29 | 4 | Not Started
|  | Feature 8 |  | Kennedy K. |  | 2022-09-24 | 2022-10-02 | 8 | Not Started
|  | Feature 9 |  | Jacob S. |  | 2022-10-02 | 2022-10-05 | 3 | Not Started

## Agile Project Plan - BLANK
AGILE PROJECT PLAN TEMPLATE
| PROJECT NAME | PROJECT MANAGER | START DATE | END DATE |  | OVERALL PROGRESS |  | PROJECT DELIVERABLE
SCOPE STATEMENT
AT RISK | TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START | FINISH | DURATION (DAYS) | STATUS | COMMENTS
Sprint 1
Feature 1
Feature 2
Feature 3
Sprint 2
Feature 4
Feature 5
Feature 6
Sprint 3
Feature 7
Feature 8
Feature 9

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.